| 2020-21 |  |
| --- | --- |
| Winter 2021 | - ISER timeline drafted |
| Spring 2021 | - ISER timeline finalized - Faculty Accreditation Coordinators appointed - Accreditation Steering Committee (ASC) reviews Lessons Learned ASC Leadership - Workgroup formed (Core Team) |
| 2021-22 |  |
| Fall 2021 | - Self-Evaluation launch and training by ACCJC - ASC determines accreditation theme and writing structure - Re-alignment of ISER Standards to governance groups and experts |
| Winter 2022 | - ISER timeline revised |
| Spring 2022 | - Update to campus community at FLEX Day - Board of Trustees accreditation training - Update to Presidents Advisory Committee - Weaving (Writing) Teams formed and trained - Monthly Accreditation Forums to engage the campus community - Weaving Teams collect evidence and submit initial drafts |
| 2022-23 |  |
| Summer 2022 | - Initial drafts edited - Review of process effectiveness - Progress update to President |
| Fall 2022 | - Update to campus community at FLEX Day & CPD-Day - Gap Analysis conducted and distributed - Weaving Teams and Review Teams read ISER draft and give feedback - Weaving Teams submit final evidence - QFE drafted |
| Winter 2023 | - Board Special Accreditation Study Session - ISER final draft created |
| Spring 2023 | - Update to campus community at FLEX Day - ISER Draft to campus community for feedback - ISER Input through forums, focus groups, and survey - Final ISER Draft Completed by 3/15 - Final draft submitted to Academic Senate, CSEA 262, CSEA 651, President, and PAC by 4/1 - Board certifies ISER by June 2023 |
| 2023-24 |  |
| Summer 2023 | - ISER released to campus community and sent to ACCJC Commission by 8/1 |
| Fall 2023 | - Update to campus community at FLEX Day & CPD Day - Formative Review: Peer Review Team reviews ISER and responds with Core Inquiries - Public Forum - ASC provides clarification on Core Inquiries to Peer Review Team - Progress update to President and PAC |
| Winter 2024 | - Summative Review: Resubmission of changes/revisions and additional information |
| Spring 2024 | - Update to campus community and Visit Preparation at FLEX Day - ACCJC Focused Site Visit March 2024 - Process evaluation and Lessons Learned |
| 2023-24 |  |
| Summer 2024 | - ACCJC Commission Decision |